School Name:- SHREE GOLMA DEVI SECONDARY SCHOOL.

Student leader name:- MAYA SUNAR AND PASANG LHAMU LAMA.

Date :- 2012 May 25th

Third Report

- Is the project completed as planned?What did you changed? Why?

- No, the project was not completed as planned because at first we decided to buy football,clock,volleyball etc but later our class friends decided that lot's of things like novel,poster,dictionary,clock,glue stick,thumb pin are needed for  the class that's why the project wasn't completed as planned.

- What was the biggest challenge? How did you solve it?

- The biggest challenge are as follows

- 1) The students of class Nine scold us because they didn't get the games to play.

- 2) The teachers also scold us by saying why didn't we gave the other students to play.

- We solve it by playing together with out fighting.

- What was the hardest part of the project?

- While asking the rate of the things was hardest part of the project because it was the first time for us and we were afraid and shy.

- What was the easiest part of the project?

- While going to bring the things was easiest part of the project because we already knew the price of the things.

- Was your budget accurate?

- No,the budget was not accurate because transportation ,food ,copy and pen expenses was not included in the budget.

- Did you spend too much money? Why?

- Yes, we spend too much of money because the transportation ,food ,copy and pen expenses was not included in the budget and we only thought about the the games and didn't thought about other things.

- Did you have money left?

- No, we don't have money let but students collaboration project has to pay us Nrs 605.

Project steps

| Steps | Task | In- charge | Date completed |
| --- | --- | --- | --- |
| 1 | Buying | MAYA SUNAR and PASANG LHAMU LAMA | May 26th |
| 2 | Implementing the project | Whole class | May 26th |

Financial Report

| Date | Item |  | Seller |  |  | Unit cost | Amount | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 05/20/12 | Football |  | Ghyalthum stationary |  |  | 1 | 1400 | 1400 |  |  |
|  | Volley ball |  | ,, |  |  | 1 | 1000 | 1000 |  |  |
|  | Novel book |  | ,, |  |  | 1 | 250 | 250 |  |  |
|  | Poster |  | ,, |  |  | 2 | 40 | 40 |  |  |
|  | Nepali – English dictionary |  | ,, |  |  | 1 | 495 | 495 |  |  |
|  | Badminton cock |  | ,, |  |  | 1 box | 140 | 140 |  |  |
|  | Glue stick |  | ,, |  |  | 1 | 60 | 60 |  |  |
|  | Thumb pin |  | ,, |  |  | 1 | 15 | 15 |  |  |
|  | cock |  | ,, |  |  | 1 | 600 | 600 |  |  |
| 04/28/12 |  | Transportation |  | (Timbu - Ghyalthum) |  | 4 | 45 |  | 180 |  |
|  | Food |  |  | Ghyalthum |  |  |  | 160 |  |  |
|  | Copy |  |  | Timbu |  | 1 | 0 | 0 |  |  |
|  | Pen |  |  | Timbu |  | 1 | 5 | 5 |  |  |
| 05/20/12 |  | Transportaion |  |  | (Timbu – Ghyalthum) | 4 | 45 |  | 180 |  |
|  |  | food |  |  | Ghyalthum |  |  |  |  | 70 |
|  |  | Total |  |  |  |  |  |  |  | 4605 |